## Roadmap
Milestone | Duration Weeks | Owner | Key Scope | Exit Criteria | Priority
M1 Foundation | 3 | Platform | Auth, profile, resume upload, dashboard shell | Secure account and resume persistence | P0
M2 Resume AI | 4 | AI | Parsing, ATS score, tailoring, cover letters | Editable AI outputs and version history | P0
M3 Jobs Pipeline | 4 | Product | Job ingestion, recommendations, Kanban, CSV export | Fresh jobs ranked and tracked | P0
M4 Controlled Apply | 5 | Automation | Approval-mode browser automation, logs, limits | Duplicate-safe audited applications | P1
M5 Interview Outreach | 3 | Growth | Interview prep, outreach, calendar integration | Templates and scheduler usable | P1

## Backlog
Epic | Story | MoSCoW | Estimate | Dependencies
Auth | Email registration and JWT login | Must | 5 | None
Profile | Career preferences and daily limits | Must | 3 | Auth
Resume | Resume upload and parsing | Must | 8 | Object storage
Resume | ATS score and keyword gap analysis | Must | 8 | AI adapter
Resume | Tailored resume version compare | Should | 8 | Resume parsing
Jobs | Fresh job ingestion and dedupe | Must | 13 | Worker queue
Jobs | Recommendation score with rationale | Must | 8 | Profile, jobs
Pipeline | Kanban board with statuses | Must | 5 | Applications API
Automation | Approval-mode form filling | Should | 13 | Playwright workers
Automation | Duplicate application prevention | Must | 5 | Applications
Interview | Q&A pack generation | Should | 5 | AI adapter
Outreach | LinkedIn and email templates | Should | 5 | Profile, jobs
Ops | Agent run logs and monitoring | Must | 8 | Worker queue

## Risks
Risk | Impact | Likelihood | Mitigation | Owner
Job-site anti-automation restrictions | High | High | Use official APIs where possible, approval mode, compliance review | Product/Legal
AI output inaccuracies | High | Medium | User review, grounded prompts, diff view, validations | AI
PII exposure | High | Medium | Encryption, tenant isolation, retention controls | Security
Worker instability | Medium | Medium | Retries, DLQ, idempotency, health checks | Platform
Over-application quality risk | Medium | High | Match thresholds, daily limits, explainability | Product

## Summary
Metric | Value
Total MVP weeks
P0 milestones
P1 milestones
Backlog story points
High impact risks